## Sheet1
Story Point Estimates
Stories | 1 Point | 2 Points | 3 Points | 5 Points | 8 Points | 13 Points | 21 Points
| 168 Lab 1 | 268 Timing Lab 8 | 268 Lab 3 Stack Testing | 268 Lab 1 Board Games | 268 Lab 7 Maze | 448 Project 1 | 448 Project 2
| 368 Assignment 1 | 268 Recursion Lab 6 | 368 Pie Chart | 268 Linked List Lab | 368 Nin Game | 368 Assignment 7
| 168 Lab 2 | 368 Assignment 2 | 168 Lab 6 Input Output | 268 Lab 4 Elevator | 168 Lab 11 DMV | 268 Pokemon Lab
448 Project 3
1 Story Point = 1 hour
Project 4 estimated to be a 21 point story
Project 4 is a larger project, more comparable to project 2 or larger.
We expect project 4 to take more time than project 3, similar to Project 2 since we are implementing a react app version of our prototype.
Code writing will take up most of our time. Probably around 16 hrs
We need to create more quizzes and functionality.
Implement quiz generator
Commenting and Documentation. Probably around 2 hrs
Then Testing and Code Review. Probably around 1 hr
Meetings. Probably around 2 hr